SOPs FOR SMALL GRANTS PROGRAM

- Under the small grant program, the faculty members of UAF may submit the proposal round the year through Dean & Director ORIC .

- Small grant support will be provided by EFS depending upon availability of funds/budget and nature of the proposal on emergent need basis.

- The small grant is expected to support short term proposals like varietal/clinical trials, prototype development, field testing and survey, Import of technology, IPRs processing fees (Patent filling, Registration of products), training of end users of related fields, etc.

- The PI/faculty member of UAF will discuss their ideas/concept with the technical staff of EFS to fine tune the proposal.

- The PI will submit his concept (1-2 Pages) illustrating the rationale, objective, team members duration (up to six months) and funds requirement at least one month before the scheduled activities. The prescribed proforma must be used.

- In the application, the PI should clearly mention the timeline for the project activities. A GANTT chart must be used for this purpose

- On the recommendation of the committee, the Vice Chancellor/Chairman BoD shall approve the funds under TT, R&D or PC component.

- After administrative approval, the PI will be allowed to execute the activity/project.

- The PI will make the expenditure partially or in total as per need according to UAF financial rules.

- After completion of the project and before submitting the report, the PI will have to give a presentation of the same before the committee in the presence of the nominated expert. The PI will then submit the completion report addressing the observations of the committee, if any.

- The PI will submit the bills to EFS for funds availability which will be forwarded to Treasurer office for audit and disbursement of funds.

- The PI will submit completion report within one month after the completion of project/activity.

- Extension of ongoing project, if needed, up to one month will be granted by Executive Director, Endowment Fund, and extension beyond one month will be got approved from Vice Chancellor/Chairman Board of Directors

- EFS will monitor small grant projects through EFS monitoring team.

- Soft copies of the report and original picture files (in JPG format will be sent at efs@uaf.edu.pk.

|  | ## ENDOWMENT FUND SECRETARIAT ## UNIVERSITY OF AGRICULTURE, FAISALABAD, PAKISTAN UAF-US COLLABORATION FOR STRENGTHENING OF AGRI. ACADEMIA Phone: 041-9201125, 9200161-170, Ext. 3604 Website: www.efsuaf.org Email: efs@uaf.edu.pk |
| --- | --- |

Proposal Identification No

(To be allotted by EFS)

PROJECT PROPOSAL

(Small Grant)

1. Project Title:

2. Applicant's Details

Note: (Only regular/TTS faculty members/researchers/scientists in UAF may apply).

| Name: |  |  |  |
| --- | --- | --- | --- |
| Qualification: |  |  |  |
| Institution/Organization: |  |  |  |
| Present Position: |  |  |  |
| Status (Regular/TTS): |  |  |  |
| Postal Address: |  |  |  |
| Tel/Mobile: |  | Email: |  |

3. Other team members

4. Total Cost (Rs. Million):

5. Location:

6. Project Duration (months):

7. Tentative Date of initiation:

8. Background/Existing Situation:

9. Justification

10. Objectives (objectives must be specific, realistic, measurable/quantifiable)

11. Methodology

Provide detailed description of the methods to be used linked to the proposed objectives.

12. Plan of work:

| Time/Duration | Activities/Description |
| --- | --- |

Give a GANTT chart also

13. Budge breakup

14. Endorsement

|  | Principal Investigator |
| --- | --- |
| Name: |  |
|  | __________________________________________ |
|  | (Seal and Signature) |
| Date: |  |

It is certified that this proposal has the concurrence and support of

| CHAIRMAN OF DEPARTMENT/ DIRECTOR OF THE INSTITUTE (Seal and Signature) |  | DEAN/HEAD (Seal and Signature) |  |
| --- | --- | --- | --- |
| Date: |  | Date: |  |